## Slide 1: Agile Principles and Practices
Agile Development Processes
Eric Knauss

## Slide 2: Announcements
Some students have joined late. Please register for group work:
  https://www.surveymonkey.com/r/EDA_397_2017
Any Roadblocks?

## Slide 3: Overview (might take 2 lectures)
Principles
Artefacts and Tools
Practices
  XP
  Scrum
  Kanban (you did watch the video, right?)
Later: Lean software development

## Slide 4: Course Objectives
Knowledge and understanding | Skills and ability | Judgement and approach
Compare agile and traditional softw. dev, | Forming a team organically | Explain: people/commun. centric dev.
Relate lean and agile development | Collaborate in small software dev. teams | Apply fact: people drive project success
Contrast different agile methodologies | Interact and show progress continuously | Describe: No single methodology fits all
Use the agile manifest and its accompanying principles | Develop SW using small and frequent iterations | Discuss: methodology needs to adopt to culture
Discuss what is different when leading an agile team | Use test-driven dev. and automated tests | 
 | Refactor a program/design | 
 | Be member of agile team | 
 | Incremental planning using user stories | 
Sprint 1
Sprint 2
Sprint 3

## Slide 5: User story
Widely accepted template: As a <role> I want to <feature> so that <customer value>
Promise to discuss this user goal further
Keep track of what the team is doing
A lot of value in physical artifact
Usually good idea to add: ID, Story Points, List of sub-tasks, Indication of customer value, notes on the backside

## Slide 6: Agile Principles – Revised list (according to [Mey2014])
Organizational
Put the customer at the center.
Let the team self-organize.
Work at a sustainable pace.
Develop minimal software:
  Produce minimal functionality.
  Produce only the product requested.
  Develop only code and tests.
Accept Change
Technical
Develop iteratively:
  Produce frequent working iterations.
  Freeze requirements during iterations.
Treat tests as a key resource:
  Do not start any new development until all tests pass.
  Test first.
Express requirements through scenarios.
6. Reflect regularly and improve continuously!
Notes: Discuss with your neighbour: Name 2 that are easy and 2 that are difficult to adhere to in your project.

## Slide 7: Agile Practices
https://techblog.betclicgroup.com/wp-content/uploads/2013/12/agileSubwayMap2.jpg
Also check: http://guide.agilealliance.org

## Slide 8: XP Principles
Rapid feedback
Assume simplicity
Incremental change
Embracing change
Quality work
Core
Less central
Teach learning
Small initial investment
Play to win
Concrete requirements
Open, honest communication
Work with people’s instincts, not against them
Accepted responsibility
Local adaptation
Travel light
Hones measurement

## Slide 9: XP Practices
Planning game
Small releases
Metaphor
Simple design
Testing (dedicated lecture)
Refactoring
Pair programming
Collective ownership
Continuous integration (dedicated lecture)
40h week
On-site customer
Coding standards

## Slide 10: Planning Game
Basic idea
  Create a rough iteration plan
  Plan next iteration in detail
Players
  Onsite Customer
  Team
  (Coach)
Moves
  Write User stories (OC + Team)
  [do some filtering]
  OC ranks US by business value [assign Fibonacci numbers]
  Team assigns story points [Planning poker]
  OC put story cards in strictly prioritized order
  Team selects the top n stories to match their velocity

## Slide 11: Pair Programming
Basic idea
  Two people on one computer
  Take one user story with them
  Review each other
  Share knowledge
Related concepts
  User story as vertical increment
  Truck factor
Sentiment in research
  Studies with contradictory results, clearly leaning towards rejecting the idea of using pair programming in general
  But Long term aspects of knowledge management not/insufficiently covered
  Good results for specific use cases (exploration, difficult task, knowledge sharing, …)

## Slide 12: Scrum Principles
Reflection
  Stop and review product & process
Self-correction
  Based on reflection
Visibility
  Everything is visible (=known) for all stakeholders, e.g. plans, schedules, issues, …

## Slide 13: Scrum practices
Product backlog vs. Sprint backlog
Sprint planning
  Planning poker: estimate cost
  ROI (Return on Investment): cost vs. benefit
Retrospective
Fixed sprint length
Burn-down charts
Daily scrum: no longer than 15min

## Slide 14: Kanban principles
Start with what you do now
Agree to pursue incremental, evolutionary change
Respect the current process, roles, responsibilities and titles
Leadership at all levels
The following is based on [KS2009]

## Slide 15: Kanban core practices
Visualize
  Visualization of workflow allows to understand and improve it
Limit Work-in-Progress
  Limit the amount of workitems for each step
  Introduce a pull-system
Manage flow
  Measure how workitems flow through the process and understand, if a change improves the situation
Make policies explicit
Implement feedback loops
  Understand (as a team) how good the process is working
Improve collaboratively, evolve experimentally
  Whole team needs to share a theory on why (small) change helps

## Slide 16: Kanban-Board
[KS2009]

## Slide 17: Limit work in progress
Prevent context switching
  Reduce multi-tasking
  performing tasks sequentially yields results sooner
Maximize throughput
Enhance teamwork
  working together to make things done
  increase cross-functionality

## Slide 18: WIP Strategy
Start with some initial value
  Small constant (1-3)
  number of developers
  number of testers
Measure the cycle time
  average time of one piece full cycle flow
Change limit to decrease cycle time

## Slide 19: Idle Members
Can you help progress an existing kanban? – Work on that.
Don’t have the right skills? – Find the bottleneck and work to release it.
Don’t have the right skills? – Pull in work from the queue.
Can’t start anything in the queue? – Check if there is any lower priority to start investigating.
There is nothing lower priority? – Find other interesting work (refactoring, tool automation, innovation).

## Slide 20: Metrics
Stories in progress (SIP)
When story enters stories queue set entry date (ED)
When story enters first process step set start processing date (SPD)
When story is done set finish date (FD)
Cycle time (CT) = FD – SPD
Waiting time (WT) = SPD – ED
Throughput (T) = SIP / CT

## Slide 21: Example
[KS2009]

## Slide 22: Example
[KS2009]

## Slide 23: Example
[KS2009]

## Slide 24: Example
[KS2009]

## Slide 25: Example
[KS2009]

## Slide 26: Example
[KS2009]

## Slide 27: Example
[KS2009]

## Slide 28: Example
[KS2009]

## Slide 29: Example
[KS2009]

## Slide 30: Example
[KS2009]

## Slide 31: Example
[KS2009]

## Slide 32: Example
[KS2009]

## Slide 33
?
Compare Kanban with your favorite agile method.
  What is similar?
  What is different?
  Is Kanban agile?

## Slide 34: Scrum vs. Kanban
[KS2009]

## Slide 35: Scrum vs. Kanban
[KS2009]

## Slide 36: Agile Principles
Early and continuous delivery of valuable software
Welcome changing requirements, even late
Deliver working software frequently
Business people and developers must work together
Build projects around motivated individuals
Face-to-face communication is most effective and efficient
Working software is the primary measure of progress
Sustainable development
Continuous attention to technical excellence and good design
Simplicity is essential
Self-organizing teams
Regular reflection
Notes: Task: For each of the principles, compare XP, Scrum, and Kanban and discuss differences
NOW: Pick two – the others might be a good exercise for exam and report.

## Slide 37: Agile Principles – Revised list (according to [Mey2014])
Organizational
Put the customer at the center.
Let the team self-organize.
Work at a sustainable pace.
Develop minimal software:
  Produce minimal functionality.
  Produce only the product requested.
  Develop only code and tests.
Accept Change
Technical
Develop iteratively:
  Produce frequent working iterations.
  Freeze requirements during iterations.
Treat tests as a key resource:
  Do not start any new development until all tests pass.
  Test first.
Express requirements through scenarios.
6. Reflect regularly and improve continuously!
Task: For each of the principles, compare XP, Scrum, and Kanban and discuss differences NOW: Pick two – the others might be a good exercise for exam and report.

## Slide 38: References
[KS2009] Henrik Kniberg and Mattias Skarin: Kanban and Scrum – Making the Most of Both. InfoQ (2009) Available online:http://infoq.com/minibooks/kanban-scrum-minibook